## Outcome 1
Regional Outcome 1
Intelligence gathering, needs assessment and analysis
Informed decisions about activities, initiatives and priorities are made based on gathered inteligence, analysed performance and assessed needs
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
1a | Gather and analyse data from NICE audit of services funded by the Association | End December 2017 and bi-annually | 2.1 | % of care centres/networks that have completed our "Transforming MND Care" audit | Will require change in contract and "reset" to start all audit requirments in 2017 | Y
1b | Gather and analyse data from NICE audit of services not funded by the Association | End December 2018 | 2.1 | Number of other services that have completed our "Transforming MND Care" audit | Will require "buy-in" to this process from service providers | Y
1c | Gather and analyse data from regional service mapping | Annually | 2.2, 2.3, 2.8 |  | Regional service mapping will target intelligence gathering for specfic services/issues | Y
1d | Gather and analyse data from patient satisfaction/experience surveys and reports | 2018 and bi-annually | 2.1 |  | Standardised patient satisfaction questionnaire being developed which will be used with services funded by the Association | Y
1e | Analysing data from Improving MND Care Survey regional reports | Annually | 2.1, 2.3, 6.3 |  | Dependent on having the resource to analyse at a regional level after 31st Dec 2016 | Y
1f | Prioritising and analysing all the available regional data and intellignece | 2017 Onwards | 6.3, 2.4 |  | The needs to be supported by a central resource for regional work | Y
1g | Identifying local campaigning issues | 30th September 2017 | 2.3, 2.4 |  | A process needs to be developed and tested
1h | Feeding intelligence about local service provision up to national policy/campaigns team | 2017 Onwards | 2.3, 2.4 |  | This is a long standing need and a process will need to be developed to do this. Without intelligence coming up from the regions it is extremely difficult for national campaigns to be developed strategically | Y

## Outcome 2
Regional Outcome 2
Driving service improvement
Improvement, delivery and development plans are created and implemented based on informed decisions (following on from outcome one)
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
2a | Creating and implementing improvement plans following NICE audits of Association-funded services | 2017 Ongoing | 2.1 | % of Care Centres/Networks that have developed an improvement plan following their audit | Timeframes as identified in individual improvement plans
2b | Supporting services that are not funded by the Association to develop improvement plans and facilitate their implementation | 2017 Ongoing | 2.1 | % of other services that have developed an improvement plan following their audit | Timeframes as identified in individual improvement plans. Communication shared form EA to RDMs | Y
2c | Using influencing and negotiation to improve health and social care services not funded by the Association where the NICE audits and/or regional service mapping has identified shortfalls | 2017 Ongoing | 2.1, 2.3, 2.4 |  | Where influencing and negotiating may include campaigning. This activity in contingent on resources for anaysis of data | Y

## Outcome 3
Regional Outcome 3
Protecting and extending care and support
PwMND, their families and carers have access to high quality health, social care and support services which meet their needs
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
3a | Managing the contract and relationships with care centres and networks | 2017 Ongoing | 2.2 | Number of care centres/networks holding steering group meetings and submitting reports as scheduled.
3b | Supporting and developing MDTs | 2017 Ongoing | 2.3
3c | Increasing the number of referrals to the Association | End December 2017 | 6.1, 5.1 | Number of pwMND known to the Association/and as a % of expected prevalence; Number of pwMND supported by a Care Volunteer on a 1-2-1 basis/and as a % of pwMND known to the Association
3d | Facilitating the delivery of a programme of regional masterclasses | End December 2017 | 3.1 |  | Needs programme agreed with Head of Education
3e | Providing training and development opportunities for HSCPs according to local needs and priorities | 2017 Ongoing | 3.1, 3.5 | Numbers of HSCPs attending regional learning and development activities
3f | Recruitment, retention and succession planning of all regionally based volunteers | 2017 Ongoing | 2.7 | Number of expressions of interest in volunteering; Number of Care Volunteers; Number of Care Volunteers recruited/left/on hold; Number of Campaigns Contacts | Includes care volunteers, campaigners, fundraising, branch and group volunteers and ways to get involved outside of formal/current volunteering opportunities. Core VDC objective
3g | Providing support and learning and development opportunities for all regionally based volunteers | 2017 Ongoing | 2.7 | % of active Care Volunteers who have completed the approved learning and development update | L&D only currently reported for care volunteers - needs further work re campaigners, fundraising and branch and group volunteers.
3h | Promoting the Champion the Charter campaign as a means to influencing local authorities and opening doors for service development | End December 2017 | 2.9 5.2 | Number of councils adopting the MND Charter
3i | Developing and delivering local campaigns where needed | 2017 Ongoing | 2.3, 2.1, 2.4, 5.2 |  | Using process developed in outcome 1
3j | Supporting the delivery of national campaigns | 2017 Ongoing | 2.3, 2.1, 2.4
3k | Promoting and increasing numbers in the Campaign Network | 2017 Ongoing | 2.1, 2.3, 2.4, 5.2, 6.2 | Number of registered members in the Campaign Network
3l | Increasing the number of B&Gs involved in campaigning | 2017 Ongoing | 2.1, 2.3, 2.4, 5.2, 6.2 | % of B&Gs involved in campaigning

## Outcome 4
Regional Outcome 4
Innovation and new work
The needs of pwMND, their families and carers are better met through innovative solutions and improved ways of working
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
4a | Developing new care volunteering roles | End Dec 2017 | 2.7 |  | New roles as agreed via care volunteer steering group and new role approval process. May have resource implications for support, learning and development of new volunteers | Y
4b | Developing new care and support services | 2017 Ongoing | 2.2, 2.3
4c | Developing and delivering IBC/innovation fund projects | 2017 Ongoing | 2.2
4d | Service user engagement /co-production and co-delivery | 2017 Ongoing | 4.1 |  | Needs a designated central budget to develop this work | Y
4e | Implementing the carers workplans, including developing local solutions | TBC | 2.8 | Number of carers known to the Association; Number of carers supported by a care volunteer on a 1-2-1 basis | Needs workplan and timescales
4f | Implementing the children and young people’s workplans, including developing local solutions | TBC | 2.8 |  | Needs workplan and timescales | ?

## Outcome 5
Regional Outcome 5
Working with others
Collaboration and the creation of effective relationships and partnerships achieves more for pwMND, their families and carers
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
5a | Mapping regional and local stakeholders and partners, analysing gaps, assessing effectiveness and prioritising involvement | Mid 2017 | 4.1, 4.2 |  | To be informed by partnership development manager's mapping exercise | Y
5b | Forming and managing relationships, partnerships and alliances and working effectively with them | 2017 onwards | 2.8, 4.1, 4.2, 6.2 |  | Includes CYP specifically under objective 2.7

## Outcome 6
Regional Outcome 6
Raising awareness, promotion and marketing
There is a greater awareness and understanding of MND, care, services and research, and of the work of the MND Association
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
6a | Promoting and marketing our resources and services to pwMND/families/carers | 2017 Onwards | 2.1, 2.5, 2.8, 6.1
6b | Promoting and marketing our online and other educational resources, events and activities to HSCPs | 2017 Onwards | 3.1, 3.2, 3.3, 3.5
6c | Raising awareness of MND and promoting the work of the MND Association with key regional stakeholders | 2017 Onwards | 4.1, 5.1, 5.2, 6.2 |  | Campaigns Manager objective to help develop stronger relationships with key national politicians by supporting volunteers to cultivate them in the regions. Cross reference with stakeholder mapping e.g. alliances, partners, politicians, policy and decision makers etc
6d | Promoting research opportunities for pwMND | 2017 Onwards | 2.6
6e | Promoting the MND Association research portfolio | 2017 Onwards | 2.6, 3.4, 6.5 |  | e.g. MND register, MirocALS, Ambrosia
6f | Working alongside the national Comms Team to identify and respond regional media opportunities | 2017 Onwards | 5.1, 5.2, 6.2
6g | Working alongside the national Conferences Team to deliver the regional conferences programme | 2017 Onwards | 2.5, 2.9, 5.1, 5.2, 6.1, 6.2

## Outcome 7
Regional Outcome 7
Fundraising
Regional Individual Fundraisers, branches and groups are empowered and enabled to maximise their fundraising potential
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
7a | Developing fundraising groups | 2017 Onwards | 6.2 | Number of new fundraising groups started | Requires VDC objectives to support this
7b | Delivering regional legacy marketing events | 2017 Onwards | 6.2 | Number of legacy marketing events held | Process design by legacy marketing manager
7c | Delivering regional thank-you events | 2017 Onwards | 6.2 | Number of thank-you events held | Consider involving other volunteer roles for example campaigners
7d | Promoting fundraising portfolio | 2017 Onwards | 6.2 | Number of Regional Individual Fundraisers (RIFs); Income raised by RIFs; Branch and group income, % of B and Gs actively claiming Gift Aid; | e.g. Silence Speaks and community fundraising activity
7e | Delivering fundraising workshops | 2017 Onwards | 6.2 |  | Branches and groups, working with VDCs
7f | Identifying and referring potential opportunities for fundraising | 2017 Onwards | 6.2 |  | Needs an agreed process for this

## Outcome 8
Regional Outcome 8
Fit-for-purpose regional systems, structures and processes
Work is planned and delivered effectively through fit for purpose regional systems, structures and processes.
No. | Activities | Timeframe | Strategic Goal & Objectives | Regional Performance Indicators (RPIs) | Comments | Additional Resource
8a | Using evidence and intelligence to inform and demonstrate the impact of our work | 2017 Onwards | 6.4 |  | Dependent on better capacity centrally | Y
8b | Implementing the diversity and equality strategy in the regions | TBC | 6.1 |  | Need strategic equality and diversity plan | ?
8c | Consultation and engagement with volunteers and key stakeholders | 2017 Onwards | 6.1, 2.7 | Cumulative % of branches and groups engaged in the LAP/LDT process; Number of HSCPs who have contributed to the development, delivery and monitoring of the LAP | Through variety of means as determined by LDTs
8d | Working collaboratively to develop and deliver work | 2017 Onwards | 4.1, 4.2 |  | Internally and externally
8e | Embedding project management | 2017 Onwards | 6.4, 6.7
8f | Agreeing and adopting a process for developing, monitoring and reviewing LAPs | 2017 Onwards | 6.7 |  | New LAPs to be completed by end Q1 2017. Agreed LAPs will run for 3 years with review after 2 1/2 years
8g | Ensuring clarity of our regional care and support offer and customer journey | TBC | 6.1 |  |  | Y
8h | Using a suite of standardised educational materials | TBC | 3.1, 3.2, 3.3 |  | To be informed by Head of Education
8i | Designing and implementing a decision-making process to select innovative ideas and projects to be taken forward | Q1 2017 | 6.4, 6.7